## Instructions
Instructions for Document G702 Application and Certificate for Payment and G703 Continuation Sheet
A. General Information
G702 Application and Certificate of Payment should be prepared and submitted in conjunction with G703 Continuation Sheet. The G703 Continuation Sheet should be completed first. Only original copies will be accepted. Faxes will be discarded.
B. Completing the G703 Continuation Form
Heading: This information will auto fill from data entered in G702 Application and Certificate for Payment.
Columns A, B & C: These columns should be completed by identifying the various portions of the project and their scheduled values consistent with the schedule of values submitted to Contractor at the commencement of the project.
Column D: Enter in this column the amount of completed work covered by the previous application (columns D & E from the previous application). Values from column F (Materials Presently Stored) from the previous application should not be entered in this column.
Column E: Enter here the value of work completed at the time of this application, including the value of materials incorporated in the project that were listed on the previous application under Materials Presently Stored (column F).
Column F: Enter here the value of Materials Presently Stored for which payment is sought. The total of the column must be recalculated at the end of each pay period. This value covers both materials newly stored for which payment is sought and materials previously stored which are not yet incorporated into the project.
Column G: This column will automatically total columns D + E + F.
Column H: This column will automatically calculate the difference between column C (Scheduled Value) and column G (Total Completed and Stored to Date).
Column I: This column will automatically calculate 10% retainage to be withheld.
Change Orders: List change orders separately under column B and complete Schedule of Values in column C.
C. Completing the G702 Application and Certificate of Payment
After completing the G703 Continuation Sheet, the G702 Application and Certificate of Payment should be completed
Heading: Complete the heading information. The Application No., Invoice No., Period To and Job No. will auto fill to the G703 form.
Change Orders: Add addition and deductive change orders approved in previous months. List all change orders approved in the current month. Only change orders approved in the current month should be listed by change order number. All previously approved invoices should be subtotalled and included in the "Change Orders Previously Approved by Contractor" section.
Billing Information: Totals will auto fill from the G703 Continuation Sheet except for Item 7. Enter the total from line 6 from the prior Certificate of Payment.
Signatures: The Subcontractor should sign and date the G702, have it notarized and submit it to Contractor along with completed G703 and all appropriate lien releases.

## G702 Application
APPLICATION AND CERTIFICATE FOR PAYMENT | [8 empty] | AIA DOCUMENT G702
TO: |  | W. L. Butler Construction, Inc. |  |  |  |  | PROJECT: |  |  |  |  | APPLICATION NO: |  |  | DISTRIBUTION TO:
5666 La Ribera St. Suite A
|  | Livermore, CA 94550 | [9 empty] | INVOICE NO: |  |  | X | CONTRACTOR
FROM: | [11 empty] | INVOICE DATE:
PERIOD TO:
CONTRACT NO: | [6 empty] | CONTRACTOR'S JOB NO: |  |  |  |  | CONTRACT DATE:
SUBCONTRACTOR'S APPLICATION FOR PAYMENT | [7 empty] | Application is made for Payment, as shown below, in connection with the Contract.
Continuation Sheet, AIA Document G703, is attached.
CHANGE ORDER SUMMARY
Change Orders approved in |  |  | ADDITIONS |  | DEDUCTIONS |  |  | 1. ORIGINAL CONTRACT SUM | [8 empty] | 0
previous months by Contractor | [7 empty] | 2. Net change by Change Orders | [8 empty] | 0
|  | TOTAL | [5 empty] | 3. CONTRACT SUM TO DATE |  |  | (Line 1+/- 2) | [5 empty] | 0
Approved this Month | [7 empty] | 4. TOTAL COMPLETED AND STORED TO DATE | [8 empty] | 0
Number | Date Approved | [7 empty] | (Column G on G703)
1 | [7 empty] | 5. RETAINAGE:
2 | [7 empty] | a. 10% of Completed Work | [5 empty] | #VALUE!
3 | [8 empty] | (Column D + E on G703)
4 | [7 empty] | b. 0% of Stored Material | [5 empty] | 0
5 | [8 empty] | (Column F on G703)
6 | [7 empty] | Total Retainage (Line 5a + 5b or
|  | TOTALS |  | 0 |  | 0 |  |  | Total in Column I of G703) | [7 empty] | #VALUE!
Net Change by Change Orders |  |  |  | 0 |  | 0 |  | 6. TOTAL EARNED LESS RETAINAGE | [8 empty] | #VALUE!
(Line 4 less Line 5 Total)
The undersigned Contractor certifies that to the best of the Contractor's knowledge, | [7 empty] | 7. LESS PREVIOUS CERTIFICATES FOR
information and belief the Work covered by this Application for Payment has been | [8 empty] | PAYMENT | (Line 6 from prior Certificate)
completed in accordance with the Contract Documents, that all amounts have been | [7 empty] | 8. CURRENT PAYMENT DUE | [8 empty] | #VALUE!
paid by the Contractor for Work for which previous Certificates for Payment were | [7 empty] | 9. BALANCE TO FINISH, PLUS RETAINAGE | [8 empty] | #VALUE!
issued and payments received from the Owner, and that current payment shown | [8 empty] | (Line 3 less Line 6)
herein is now due. | [7 empty] | State of California | [5 empty] | County of
Subscribed and sworn to before me this
SUBCONTRACTOR: | [7 empty] | Notary Public:
My Commission Expires:
By: |  |  |  |  | Date: |  |  | Witness my hand and official seal:
APPLICATION FOR PAYMENT CHECKLIST - TO BE COMPLETED BY CONTRACTOR
NOTE: PAYMENT WILL BE DELAYED IF APPLICATION IS NOT ACCURATE, IF ITEMS ARE MISSING OR IF UNAPPROVED CHANGE ORDERS ARE BILLED.
WLB Project Accountant: Check list below for completeness. If items are missing, contact Subcontractor for completion before approval is given to Project Manager. | [5 empty] | Approved By: |  |  | Gross: |  |  |  | Notes for Subcontractor:
[6 empty] | Invoice #: |  |  | Retention: |  |  |  | Only bill for change orders that have been approved by Contractor. Billing for unapproved change orders may result in invoice being kicked back for revision and eliminated from current billing to owner.
Original Application | [5 empty] | Date: |  |  | Discount:
Original Continuation Sheet
Conditional Lien Release | [12 empty] | Attach all appropriate Supplier and Subcontractor lien releases with completed Application for Payment.
Unconditional Supplier Releases | [5 empty] | Job # | CSI # |  | Type | Amount
Conditional Supplier Releases
Note on A22: For change orders 7 and up replace "1,2,3,4,5,6" with "7,8,9,1,0,11,12"
Note on A23: For change orders 7 and up replace "1,2,3,4,5,6" with "7,8,9,1,0,11,12"
Note on A24: For change orders 7 and up replace "1,2,3,4,5,6" with "7,8,9,1,0,11,12"
Note on A25: For change orders 7 and up replace "1,2,3,4,5,6" with "7,8,9,1,0,11,12"
Note on A26: For change orders 7 and up replace "1,2,3,4,5,6" with "7,8,9,1,0,11,12"
Note on A27: For change orders 7 and up replace "1,2,3,4,5,6" with "7,8,9,1,0,11,12"
Note on B22: Enter date change order was issued.
Note on B23: Enter date change order was issued.
Note on B24: Enter date change order was issued.
Note on B25: Enter date change order was issued.
Note on B26: Enter date change order was issued.
Note on B27: Enter date change order was issued.
Note on B40: Subcontractor's authorized agent should sign invoice
Note on C7: Enter Subcontractor's name, address, phone and fax numbers
Note on C12: Enter Contract Number
Note on E19: Enter total positive change orders approved in previous months
Note on E22: Enter amount for corresponding change order
Note on E23: Enter amount for corresponding change order
Note on E24: Enter amount for corresponding change order
Note on E25: Enter amount for corresponding change order
Note on E26: Enter amount for corresponding change order
Note on E27: Enter amount for corresponding change order
Note on G19: Enter total deductive change orders approved in previous months.
Note on G22: Enter amount for corresponding deductive change order
Note on G23: Enter amount for corresponding deductive change order
Note on G24: Enter amount for corresponding deductive change order
Note on G25: Enter amount for corresponding deductive change order
Note on G26: Enter amount for corresponding deductive change order
Note on G27: Enter amount for corresponding deductive change order
Note on G40: Insert date invoice was signed in this cell.
Note on J3: Enter project name and address
Note on J12: Enter W. L. Butler's job number
Note on M38: Notary's signature here
Note on N37: Enter date application is signed
Note on N39: Enter date notary's commissino expires in this cell.
Note on P3: Enter your application number
Note on P5: Enter your unique invoice number. Each invoice must have a unique number.
Note on P7: Enter date of invoice.
Note on P9: Enter billing end period.
Note on P12: Enter date of original contract.
Note on S36: Insert county where notary is commissioned
Note on T17: Insert Original Contract Amount in this cell.
Note on T32: You must manually enter an amount from the Previous Application. This will be the net amount previously billed.
Project
Mgr
Const
Mgr
Vice
Pres
Contract
Coord

## G703 Continuation
CONTINUATION SHEET |  |  |  | AIA DOCUMENT G703 |  |  |  | PAGE OF PAGES | 2 of 2
AIA Document G702, APPLICATION AND CERTIFICATION FOR PAYMENT, containing | [6 empty] | APPLICATION NO:
Subcontractor's signed certification is attached. | [6 empty] | INVOICE NO:
INVOICE DATE:
SUBCONTRACTOR: |  | 0 |  |  |  |  | PERIOD TO:
A | B | C | D | E | F | G |  | H | I
ITEM | DESCRIPTION OF WORK | SCHEDULED | WORK COMPLETED |  | MATERIALS | TOTAL | % | BALANCE | RETAINAGE
NO. |  | VALUE | FROM PREVIOUS | THIS PERIOD | PRESENTLY | COMPLETED | (G ÷ C) | TO FINISH
|  |  | APPLICATION |  | STORED | AND STORED |  | (C - G)
|  |  | (D + E) |  | (NOT IN | TO DATE
[5 empty] | D OR E) | (D+E+F)
[8 empty] | #VALUE! | #VALUE!
[8 empty] | #VALUE! | #VALUE!
[8 empty] | #VALUE! | #VALUE!
[8 empty] | #VALUE! | #VALUE!
[8 empty] | #VALUE! | #VALUE!
[8 empty] | #VALUE! | #VALUE!
[8 empty] | #VALUE! | #VALUE!
[8 empty] | #VALUE! | #VALUE!
[8 empty] | #VALUE! | #VALUE!
[8 empty] | #VALUE! | #VALUE!
[8 empty] | #VALUE! | #VALUE!
[8 empty] | #VALUE! | #VALUE!
[8 empty] | #VALUE! | #VALUE!
[8 empty] | #VALUE! | #VALUE!
[8 empty] | #VALUE! | #VALUE!
[8 empty] | #VALUE! | #VALUE!
[6 empty] | 0 | 0 | 0
| GRAND TOTALS | 0 | 0 | 0 | 0 | 0 | 0.00% | #VALUE! | #VALUE!
Only bill for change orders that have been approved by Contractor. Billing for unapproved change orders may result in invoice being kicked back for revision and eliminated from current billing to owner.
Attach all appropriate Supplier and Subcontractor lien releases with completed Application for Payment.
Note on B8: Enter each line item breakdown as per your Subcontract Agreement
Note on B12: W.L. Butler: If additional rows are needed insert and check to make sure that calculations are correct.
Note on C8: Enter the schedule of values as per your Subcontract Agreement
Note on D9: Enter the amount of completed work covered by previous application (columns D and E from the previous application).
Note on E9: Enter the value of work completed at the time of this application.
Note on G8: Will auto calculate columns D+E+F
Note on I2: Application No. will automatically fill from G702
Note on I3: Invoice No. will automatically fill from G702
Note on I4: Invoice Date will automatically feed from G702
Note on I5: Period To will automatically feed from G702
Note on I8: Will auto calculate the balance to finish
Note on J8: Will auto calculate a 10% retention withholding

## G702 Application SAMPLE
APPLICATION AND CERTIFICATE FOR PAYMENT | [8 empty] | AIA DOCUMENT G702
TO: |  | W. L. Butler Construction, Inc. |  |  |  |  | PROJECT: | Almight Shopping Center |  |  |  | APPLICATION NO: |  | 3 | DISTRIBUTION TO:
|  | 204 Franklin Street | [5 empty] | 1245 Sunset Lane
|  | Redwood City, CA 94063 | [5 empty] | Irvine, CA 95618 |  |  |  | INVOICE NO: |  | 45886 | X | CONTRACTOR
FROM: |  | ACME Subcontractors, Inc. | [9 empty] | INVOICE DATE: |  | 2003-06-25
123 Buckleshoe Court
|  | San Diego, CA 95412 | [9 empty] | PERIOD TO: |  | 2003-06-30
CONTRACT NO: |  | 23004-3100 |  |  |  |  | CONTRACTOR'S JOB NO: | 23004 |  |  |  | CONTRACT DATE: |  | 2003-05-01
SUBCONTRACTOR'S APPLICATION FOR PAYMENT | [7 empty] | Application is made for Payment, as shown below, in connection with the Contract.
Continuation Sheet, AIA Document G703, is attached.
CHANGE ORDER SUMMARY
Change Orders approved in |  |  | ADDITIONS |  | DEDUCTIONS |  |  | 1. ORIGINAL CONTRACT SUM | [8 empty] | 105000
previous months by Contractor | [7 empty] | 2. Net change by Change Orders | [8 empty] | 26950
|  | TOTAL |  | 22700 |  |  |  | 3. CONTRACT SUM TO DATE |  |  | (Line 1+/- 2) | [5 empty] | 131950
Approved this Month | [7 empty] | 4. TOTAL COMPLETED AND STORED TO DATE | [8 empty] | 106950
Number | Date Approved | [7 empty] | (Column G on G703)
3 | 2003-06-01 |  |  | 3500 |  |  |  | 5. RETAINAGE:
4 | 2003-06-05 |  |  |  |  | -1750 |  | a. 10% of Completed Work | [5 empty] | #VALUE!
5 |  |  |  | 2500 |  |  |  |  | (Column D + E on G703)
[8 empty] | b. 0% of Stored Material | [5 empty] | 0
(Column F on G703)
Total Retainage (Line 5a + 5b or
|  | TOTALS |  | 6000 |  | -1750 |  |  | Total in Column I of G703) | [7 empty] | #VALUE!
Net Change by Change Orders |  |  |  | 28700 |  | -1750 |  | 6. TOTAL EARNED LESS RETAINAGE | [8 empty] | #VALUE!
(Line 4 less Line 5 Total)
The undersigned Contractor certifies that to the best of the Contractor's knowledge, | [7 empty] | 7. LESS PREVIOUS CERTIFICATES FOR
information and belief the Work covered by this Application for Payment has been | [8 empty] | PAYMENT | (Line 6 from prior Certificate) | [6 empty] | 56430
completed in accordance with the Contract Documents, that all amounts have been | [7 empty] | 8. CURRENT PAYMENT DUE | [8 empty] | #VALUE!
paid by the Contractor for Work for which previous Certificates for Payment were | [7 empty] | 9. BALANCE TO FINISH, PLUS RETAINAGE | [8 empty] | #VALUE!
issued and payments received from the Owner, and that current payment shown | [8 empty] | (Line 3 less Line 6)
herein is now due. | [7 empty] | State of California | [5 empty] | County of |  | San Diego
[8 empty] | Subscribed and sworn to before me this |  |  |  | 2003-06-25
SUBCONTRACTOR: | [7 empty] | Notary Public: |  |  | Gina M Tankersley
[8 empty] | My Commission Expires: |  |  | 2005-06-13
By: | Wyle E. Coyote |  |  |  | Date: | 2003-06-25 |  | Witness my hand and official seal: |  |  |  |  | Gina M. Tankersley
APPLICATION FOR PAYMENT CHECKLIST - TO BE COMPLETED BY CONTRACTOR
NOTE: PAYMENT WILL BE DELAYED IF APPLICATION IS NOT ACCURATE, IF ITEMS ARE MISSING OR IF UNAPPROVED CHANGE ORDERS ARE BILLED.
WLB Project Accountant: Check list below for completeness. If items are missing, contact Subcontractor for completion before approval is given to Project Manager. | [5 empty] | Approved By: |  |  | Gross: |  |  |  | Notes for Subcontractor:
[6 empty] | Invoice #: |  |  | Retention: |  |  |  | Only bill for change orders that have been approved by Contractor. Billing for unapproved change orders may result in invoice being kicked back for revision and eliminated from current billing to owner.
Original Application | [5 empty] | Date: |  |  | Discount:
Original Continuation Sheet
Conditional Lien Release | [12 empty] | Attach all appropriate Supplier and Subcontractor lien releases with completed Application for Payment.
Unconditional Supplier Releases | [5 empty] | Job # | CSI # |  | Type | Amount
Conditional Supplier Releases
Note on A22: For change orders 7 and up replace "1,2,3,4,5,6" with "7,8,9,1,0,11,12"
Note on A23: For change orders 7 and up replace "1,2,3,4,5,6" with "7,8,9,1,0,11,12"
Note on A24: For change orders 7 and up replace "1,2,3,4,5,6" with "7,8,9,1,0,11,12"
Note on A25: For change orders 7 and up replace "1,2,3,4,5,6" with "7,8,9,1,0,11,12"
Note on A26: For change orders 7 and up replace "1,2,3,4,5,6" with "7,8,9,1,0,11,12"
Note on A27: For change orders 7 and up replace "1,2,3,4,5,6" with "7,8,9,1,0,11,12"
Note on B22: Enter date change order was issued.
Note on B23: Enter date change order was issued.
Note on B24: Enter date change order was issued.
Note on B25: Enter date change order was issued.
Note on B26: Enter date change order was issued.
Note on B27: Enter date change order was issued.
Note on B40: Subcontractor's authorized agent should sign invoice
Note on C7: Enter Subcontractor's name, address, phone and fax numbers
Note on C12: Enter Contract Number
Note on E19: Enter total positive change orders approved in previous months
Note on E22: Enter amount for corresponding change order
Note on E23: Enter amount for corresponding change order
Note on E24: Enter amount for corresponding change order
Note on E25: Enter amount for corresponding change order
Note on E26: Enter amount for corresponding change order
Note on E27: Enter amount for corresponding change order
Note on G19: Enter total deductive change orders approved in previous months.
Note on G22: Enter amount for corresponding deductive change order
Note on G23: Enter amount for corresponding deductive change order
Note on G24: Enter amount for corresponding deductive change order
Note on G25: Enter amount for corresponding deductive change order
Note on G26: Enter amount for corresponding deductive change order
Note on G27: Enter amount for corresponding deductive change order
Note on G40: Insert date invoice was signed in this cell.
Note on J3: Enter project name and address
Note on J12: Enter W. L. Butler's job number
Note on M38: Notary's signature here
Note on M39: Enter date notary's commissino expires in this cell.
Note on N37: Enter date application is signed
Note on P3: Enter your application number
Note on P5: Enter your unique invoice number. Each invoice must have a unique number.
Note on P7: Enter date of invoice.
Note on P9: Enter billing end period.
Note on P12: Enter date of original contract.
Note on S36: Insert county where notary is commissioned
Note on T17: Insert Original Contract Amount in this cell.
Note on T32: You must manually enter an amount from the Previous Application. This will be the net amount previously billed.
Project
Mgr
Const
Mgr
Vice
Pres
Contract
Coord

## G703 Continuation SAMPLE
CONTINUATION SHEET |  |  |  | AIA DOCUMENT G703 |  |  |  | PAGE OF PAGES | 2 of 2
AIA Document G702, APPLICATION AND CERTIFICATION FOR PAYMENT, containing | [6 empty] | APPLICATION NO: | 3
Subcontractor's signed certification is attached. | [6 empty] | INVOICE NO: | 45886
[7 empty] | INVOICE DATE: | 2003-06-25
SUBCONTRACTOR: |  | ACME Subcontractors, Inc. |  |  |  |  | PERIOD TO: | 2003-06-30
A | B | C | D | E | F | G |  | H | I
ITEM | DESCRIPTION OF WORK | SCHEDULED | WORK COMPLETED |  | MATERIALS | TOTAL | % | BALANCE | RETAINAGE
NO. |  | VALUE | FROM PREVIOUS | THIS PERIOD | PRESENTLY | COMPLETED | (G ÷ C) | TO FINISH
|  |  | APPLICATION |  | STORED | AND STORED |  | (C - G)
|  |  | (D + E) |  | (NOT IN | TO DATE
[5 empty] | D OR E) | (D+E+F)
2520 | Concrete Paving/Sidewalks | 15000 | 5000 | 7500 |  | 12500 | 83.33% | 2500 | 1250
2520 | Concrete Paving | 10000 | 5000 | 5000 |  | 10000 | 100% |  | 1000
3011 | Concrete Slab on Grade | 15000 | 5000 | 5000 |  | 10000 | 66.67% | 5000 | 1000
3322 | Footing Concrete | 55000 | 20000 | 20000 |  | 40000 | 72.73% | 15000 | 4000
3442 | Tilt-Up Wall Panels | 10000 | 10000 | 0 |  | 10000 | 100% |  | 1000
| Change Order 1 | 15200 | 15200 | 0 |  | 15200 | 100% |  | 1520
| Change Order 2 | 7500 | 2500 | 2500 |  | 5000 | 66.67% | 2500 | 500
| Change Order 3 | 3500 |  | 3500 |  | 3500 | 100% |  | 350
| Change Order 4 | -1750 |  | -1750 |  | -1750 | 100% |  | -175
| Change Order 5 | 2500 |  | 2500 |  | 2500 | 100% |  | 250
[8 empty] | #VALUE! | #VALUE!
[8 empty] | #VALUE! | #VALUE!
[8 empty] | #VALUE! | #VALUE!
[8 empty] | #VALUE! | #VALUE!
[8 empty] | #VALUE! | #VALUE!
[8 empty] | #VALUE! | #VALUE!
[6 empty] | 0 | 0 | 0
| GRAND TOTALS | 131950 | 62700 | 44250 | 0 | 106950 | 81.05% | #VALUE! | #VALUE!
Only bill for change orders that have been approved by Contractor. Billing for unapproved change orders may result in invoice being kicked back for revision and eliminated from current billing to owner.
Attach all appropriate Supplier and Subcontractor lien releases with completed Application for Payment.
Note on B8: Enter each line item breakdown as per your Subcontract Agreement
Note on B12: W.L. Butler: If additional rows are needed insert and check to make sure that calculations are correct.
Note on C8: Enter the schedule of values as per your Subcontract Agreement
Note on D9: Enter the amount of completed work covered by previous application (columns D and E from the previous application).
Note on E9: Enter the value of work completed at the time of this application.
Note on G8: Will auto calculate columns D+E+F
Note on I2: Application No. will automatically fill from G702
Note on I3: Invoice No. will automatically fill from G702
Note on I4: Invoice Date will automatically feed from G702
Note on I5: Period To will automatically feed from G702
Note on I8: Will auto calculate the balance to finish
Note on J8: Will auto calculate a 10% retention withholding